## Slide 1: GCP Migration Program: Monthly Stakeholder Report
Month 4 · end of week 17
For the executive sponsor and steering committee. Figures are illustrative.
Prepared by Balakrishna Pallapolu, program lead

## Slide 2: Month 4 is amber; the end date holds
AMBER
9 of 20 applications live against a plan of 10
Wave 1 moved 7 of its 8 applications on schedule with no rollbacks. One Tier 1 application, A-07, failed its cutover rehearsal: the final database sync took 5 hours 40 minutes against a 4-hour window. It is rescheduled to week 18. Wave 2 is on plan and the week 26 end date holds.
9 of 20
applications live; plan was 10
9 of 9
first-time cutovers, no rollbacks
0
open Severity 1 or 2 incidents
61%
of budget spent; plan was 59%
Decision needed
Approve one six-hour weekend window for A-07 in week 18. The alternative is a phased database migration that adds two weeks and uses all remaining contingency.
Achieved this month
Seven Platform A applications cut over, two of them Tier 1
One Severity 2 incident in hypercare, closed in three days
Average cutover time down from 3h 10m to 2h 20m

## Slide 3: One application is two weeks behind plan
Milestone | Planned | Forecast | Status | Comment
M1 Mobilize and discover | Week 4 | Done week 4 | Complete | Baseline approved
M2 Foundations ready | Week 8 | Done week 8 | Complete | Security sign-off received
M3 Pilot | Week 10 | Done week 10 | Complete | Re-forecast confirmed the plan
M4 Wave 1: Platform A | Week 16 | Week 18 | Amber | 7 of 8 live; A-07 outstanding
M5 Wave 2: Platform B | Week 22 | Week 22 | Green | 6 of 10 builds complete; cutovers start week 18
M6 Resilience proven | Week 24 | Week 24 | Not started | Exercise scenario in draft
M7 Stabilize and hand over | Week 26 | Week 26 | Not started | Starts week 24
Green: on plan. Amber: a gate is at risk and has a recovery path. Red: a gate will be missed without a steering decision.

## Slide 4: Migration is one application short of plan
Chart: Applications live on GCP, cumulative
| Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6
Planned | 0 | 2 | 2 | 10 | 20 | 20
Actual | 0 | 2 | 2 | 9
Measure | This month | Target
First-time cutover success | 9 of 9 | At least 90%
Rehearsals inside the window | 9 of 10 | All before go
Zone failover tests passed | 9 of 9 | All live
Peak Tier 1 replica lag | 40 seconds | Under 5 minutes
Open Severity 1 and 2 | 0 | 0
Spend to date | 61% | 59% planned
Contingency used | 0 of 2 weeks | Steering approval
Remaining migration contingency is now earmarked for A-07.

## Slide 5: Three risks and issues need attention
Item | Type | Status | Action | Owner
A-07 cutover exceeds its 4-hour window | Issue | Amber | Replication re-tuned; second rehearsal in week 17 ran 5 hours 10 minutes; six-hour window requested | Database lead
Platform B team at 22 percent capacity against 30 percent agreed | Risk | Amber | Raised with sponsor; two features proposed for deferral | Executive sponsor
Business owners not yet confirmed for the DR exercise in week 23 | Risk | Green | Invitations issued; confirmation due week 19 | SRE lead

## Slide 6: Two decisions, then the final wave
Decisions needed
1. Approve a six-hour weekend window for A-07 in week 18.
The alternative is a phased database migration, which adds two weeks and uses all remaining contingency.
2. Confirm Platform B team capacity at 30 percent through week 21.
Without it, Tier 1 cutovers in weeks 20 to 21 are at risk.
Next month
Cut over A-07 and all 10 Platform B applications, weeks 18 to 21
Approve the DR exercise plan and start load testing
Reach gate G5: all 20 applications live by week 22