## Slide 1: GCP Migration Program Approach
20 applications, two platforms, 26 weeks
Scenario 1 · Program planning
Balakrishna Pallapolu

## Slide 2: All 20 applications live by week 22
Replatform, do not redesign. Applications move in three waves ordered by dependency and risk, each using one repeatable cutover pattern. Resilience is tested inside every wave, not left to the end.
What I commit to as program owner
20 applications and their databases in production on GCP by week 22
Recovery targets agreed in week 3 and demonstrated by week 24
A gate at the end of every milestone; a go/no-go and a tested rollback for every cutover
Any threat to the end date raised within a week of discovery
20
applications across two platforms
3
waves: pilot, Platform A, Platform B
Week 24
HA and DR proven in a full exercise
2 weeks
contingency held at program level
Holds on three conditions: no material application refactoring · key decisions closed by week 4 · committed team capacity

## Slide 3: What the brief leaves open, and what I assumed
Open question | Assumption | If wrong | Confirmed by
Why are the platforms complex? | Shared databases and batch jobs; integrations cross both platforms | Larger move groups; fewer, bigger cutovers | Traffic analysis, week 3
Can applications move as they are? | On-premises source; 16 of 20 containerize without code change; the rest rehost on VMs | Each refactor adds about 3 weeks | Fitness review, week 3
How critical, what recovery? | 6 Tier 1 (RTO 1 hour, RPO 5 minutes), 9 Tier 2 (4 hours, 15 minutes), 5 Tier 3 (24 hours) | Tighter targets need active-active | Business sign-off, week 3
What regulation applies? | Regulated financial data; US regions only; audit evidence at every gate | A new approval step before G2 | Security and risk review, week 2
How much downtime? | Tier 1: one 4-hour weekend window. Tier 2 and 3: a weeknight window | Zero downtime needs another pattern | Business sign-off, week 4
Who does the work? | Two squads of six, a platform team of five, 30 percent of each application team | A third squad or less scope is needed | Sponsor commitment, week 4
What constrains the calendar? | One change freeze of up to two weeks, assumed in weeks 12 to 13 when no cutovers are planned; dual running is funded | A freeze elsewhere uses contingency | Change calendar, week 4

## Slide 4: Replatform onto managed GCP services
Layer | Target
Java and modern .NET | Containers on regional GKE clusters
Legacy .NET Framework | Windows VMs in regional managed instance groups
PostgreSQL | Cloud SQL, regional HA, cross-region replica
Data migration | Database Migration Service, continuous replication
Network | Shared VPC, interconnect, VPN as backup
Delivery and operations | One pipeline, infrastructure as code, central monitoring
Disaster recovery by tier
Tier 1 · 6 applications
Warm standby in a second region
RTO 1 hour · RPO 5 minutes
Tier 2 · 9 applications
Pilot light: live replica, compute rebuilt from code
RTO 4 hours · RPO 15 minutes
Tier 3 · 5 applications
Restore from cross-region backup
RTO 24 hours · RPO 24 hours
All tiers run across multiple zones with automatic database failover. The 5-minute RPO is measured under load in the pilot, because the cross-region replica is asynchronous.

## Slide 5: One cutover pattern, repeated 20 times
1
Build
T minus 3 weeks
Infrastructure from code; application in non-production; replication started
2
Test
T minus 2 weeks
Functional, integration, performance and security tests on the target
3
Rehearse
T minus 1 week
Full cutover and rollback with production-sized data, timed
4
Cut over
T
Go/no-go, stop writes, final sync, reconcile data, switch traffic, validate
5
Hypercare
T plus 2 weeks
Squad stays on call; source kept read-only for 30 days for reconciliation, not failback
Rollback: a decision point at T plus 2 hours. Before it, traffic returns to the source. After it, the team fixes forward.
A common pattern is what makes 20 cutovers in 13 weeks credible: every team learns it once, and each rehearsal produces a measured duration before any go decision.

## Slide 6: Seven milestones over 26 weeks
W2
W4
W6
W8
W10
W12
W14
W16
W18
W20
W22
W24
W26
M1 Mobilize and discover
G1
M2 Foundations ready
G2
M3 Pilot: 2 applications
G3
M4 Wave 1: Platform A
G4
M5 Wave 2: Platform B
G5
M6 Resilience proven
G6
M7 Stabilize and hand over
G7
Week 22: all 20 applications in production, four weeks before close. Diamonds mark gates. Cutovers finish in week 21, leaving contingency before G5 and before G7.
Critical path: interconnect and security sign-off, G2, pilot cutover, G3, Wave 1, Wave 2 Tier 1 cutovers, DR exercise, G6.

## Slide 7: M1 Mobilize and discover: weeks 1 to 4
Replace assumptions with facts and baseline a plan the sponsors sign.
Activity | Owner | Weeks | Output
Confirm sponsor, governance and decision rights | Program lead | 1 | Charter, responsibility matrix
Order interconnect; open security baseline review | Platform and security leads | 1 | Order placed; review booked
Inventory 20 applications and their dependencies | Application leads | 1 to 3 | Inventory, dependency map
Decide containerize or rehost; check databases | Platform and database leads | 2 to 3 | Disposition per application
Agree tiers and recovery targets | Program lead, business owners | 3 | Signed tiering
Define move groups, wave plan, capacity, budget | Program lead | 3 to 4 | Baselined plan
Approve target architecture and DR design | Cloud platform lead | 4 | Architecture decision record
Exit gate: G1 Baseline approved, week 4: inventory and dependency map complete; tiers and recovery targets signed; plan and budget baselined.
Lever if late: baseline Wave 1 only and finish Platform B discovery during foundations.

## Slide 8: M2 Foundations ready: weeks 3 to 8
A secure, observable landing zone that any application can be deployed to from code.
Activity | Owner | Weeks | Output
Build landing zone as code in two regions | Cloud platform lead | 3 to 6 | Landing zone
Bring up VPN, then interconnect | Cloud platform lead | 4 to 7 | Hybrid connectivity
Build CI/CD pipeline and base images | Cloud platform lead | 4 to 7 | One pipeline, three templates
Define database, replication and backup patterns | Database lead | 5 to 7 | Reusable database module
Set up logging, monitoring and alerting | SRE lead | 5 to 8 | Operations baseline
Security review and penetration test | Security lead | 7 to 8 | Sign-off
Deploy a reference application end to end | Cloud platform lead | 8 | Working proof
Exit gate: G2 Foundations accepted, week 8: security sign-off; interconnect live; pipeline deploys a reference application.
Lever if late: the pilot proceeds over VPN; Wave 1 does not start without the interconnect.

## Slide 9: M3 Pilot, 2 applications: weeks 7 to 10
Prove the cutover pattern on one .NET and one Java Tier 3 application, and measure what was only estimated.
Activity | Owner | Weeks | Output
Build both applications in non-production | Squad 1 | 7 | Target environments
Functional, integration and performance tests | Test lead | 8 | Test report
Rehearse cutover and rollback, timed | Squad 1, database lead | 8 to 9 | Measured durations
Production cutover, after G2 | Program lead runs go/no-go | 9 | Two applications live
Zone failover test; DR dry run; replica lag | SRE lead | 9 to 10 | Resilience evidence
Retrospective; update runbook and estimates | Program lead | 10 | Runbook version 1; re-forecast
Exit gate: G3 Pilot live, week 10: two applications in production; cutover and rollback rehearsed; zone failover passed; re-forecast issued.
Lever if late: effort more than 25 percent over estimate goes to steering as a re-plan.

## Slide 10: M4 Wave 1, Platform A: weeks 11 to 16
Move the remaining 8 Platform A applications, reaching 10 of 20 in production.
Activity | Owner | Weeks | Output
Build 8 applications; start replication | Squads 1 and 2, Platform A lead | 11 to 12 | Target environments
Test each move group | Test lead | 12 to 14 | Test reports
Rehearse each cutover and rollback | Squads, database lead | 13 to 15 | Timings inside the window
Cut over Tier 3 and Tier 2 on weeknights | Program lead runs go/no-go | 14 to 15 | 5 applications live
Cut over Tier 1 at weekends | Program lead runs go/no-go | 15 to 16 | 3 applications live
Zone failover test per application | SRE lead | 14 to 16 | HA evidence
Exit gate: G4 Platform A complete, week 16: 10 applications in production; no open Severity 1 or 2 defects.
Lever if late: a move group that fails rehearsal joins the Wave 2 schedule and does not delay the wave.

## Slide 11: M5 Wave 2, Platform B: weeks 15 to 22
Move all 10 Platform B applications, reaching 20 of 20 in production.
Activity | Owner | Weeks | Output
Build 10 applications; start replication | Squads 1 and 2, Platform B lead | 15 to 18 | Target environments
Test each move group | Test lead | 16 to 19 | Test reports
Rehearse each cutover and rollback | Squads, database lead | 17 to 20 | Timings inside the window
Cut over Tier 3 and Tier 2 on weeknights | Program lead runs go/no-go | 18 to 20 | 7 applications live
Cut over Tier 1 at weekends | Program lead runs go/no-go | 20 to 21 | 3 applications live
Source set read-only and retained; contingency before G5 | Program lead | 22 | Evidence for gate G5
Exit gate: G5 All applications live, week 22: 20 applications in production; source read-only and retained.
Lever if late: the contingency before G5 absorbs one slip. A second slip goes to steering: add a squad, or defer a Tier 3 application.

## Slide 12: M6 Resilience proven: weeks 21 to 24
Demonstrate, with evidence, that the target meets its recovery targets.
Activity | Owner | Weeks | Output
Approve DR exercise scenario and criteria | SRE lead, business owners | 21 | Exercise plan
Load test the full estate at peak volume | Test lead | 21 to 22 | Performance report
Regional failover exercise, Tier 1 and 2 | SRE lead | 23 | Measured RTO and RPO
Timed backup restore for Tier 3 | Database lead | 23 | Measured restore time
Fail back; fix findings; retest | SRE lead | 24 | Closed findings
Assemble evidence pack for risk and audit | Program lead | 24 | Evidence pack
Exit gate: G6 Resilience proven, week 24: DR exercise meets recovery targets; performance within 10 percent of baseline.
Lever if late: a missed target is fixed and retested for that application only.

## Slide 13: M7 Stabilize and hand over: weeks 24 to 26
Operations owns the platform, and the program can close.
Activity | Owner | Weeks | Output
Hypercare for the final wave; defect burn-down | Squads 1 and 2 | 24 to 25 | No open Severity 1 or 2
Hand over runbooks, on-call and dashboards | SRE lead | 24 to 25 | Signed handover
Set cost baseline and optimization backlog | Finance partner, platform lead | 25 | Run-cost baseline
Agree dated decommission plan for the source | Program lead | 25 | Approved plan
Closure report and lessons learned | Program lead | 25 to 26 | Closure report
Exit gate: G7 Program closed, week 26: operations accepts handover; decommission plan approved.
Lever if late: low-severity defects move to application team backlogs with named owners.

## Slide 14: The work fits, with 18 percent headroom
140
person-weeks of demand
20 applications at 7 person-weeks each
171
person-weeks of supply
228 gross, 75 percent productive
31
person-weeks of headroom
about four applications of slack
Supply | Calculation | Person-weeks
Squad 1 | 6 people, weeks 5 to 25 | 126
Squad 2 | 6 people, weeks 9 to 25 | 102
Gross |  | 228
Productive | 75 percent, after onboarding, hypercare and DR exercise support | 171
The 7 person-week estimate is the assumption the pilot tests. At 25 percent over, demand reaches 175 and exceeds supply. That is why a 25 percent overrun at gate G3 goes to the steering committee as a re-plan.
The platform team of five and the 30 percent contribution from application teams are in addition, and are not counted here. Peak load is three to four cutovers a week in weeks 14 to 15 and 19 to 20.

## Slide 15: Six measures, each with a target, trigger and response
Measure | Target | Trigger | Response | Decided by
Applications live against plan | On or ahead of plan | Two or more behind | Re-sequence move groups; then draw contingency | Program lead, then steering
First-time cutover success | At least 90 percent | Any rollback | Cause fixed before the next similar cutover | Program lead
Rehearsal inside the window | All, before any go | Any rehearsal over its window | No go. Re-tune or request a longer window | Database lead, business owner
Severity 1 and 2 in hypercare | Zero at each gate | Any open at a gate | The gate does not pass | Steering committee
Recovery targets in test | All Tier 1 and 2 by week 24 | Any target missed | Fix and retest that application only | SRE lead
Spend against plan | Within 5 percent | More than 5 percent over | Options to steering within a week | Program lead, finance partner
Rhythm: daily wave stand-up, weekly program review of these measures, go/no-go before every cutover, steering every two weeks, stakeholder report monthly.

## Slide 16: Six risks most likely to threaten the date
Risk | Likelihood / impact | What this plan does about it | Owner | Seen first-hand
Undocumented dependencies surface at cutover | High / High | Traffic analysis in discovery, covering vendor and external calls; not interviews alone | Application leads | An external vendor API that nobody had listed
Application teams pulled back to other work | High / High | Capacity is a sponsor decision by week 4; regulatory and freeze dates are on the wave plan | Executive sponsor | A regulatory deadline took the team
Database cutover exceeds its window | Medium / High | Every cutover rehearsed with production-sized data and timed; over the window means no go | Database lead | A migration overran by over a week
Security or audit sign-off arrives late | Medium / High | Security lead embedded from week 1; patterns approved once; evidence at every gate | Security lead | Sign-off arrived late
Legacy .NET cannot be containerized | Medium / Medium | Decide per application by week 3; rehost on virtual machines | Cloud platform lead | A legacy app needed rework before moving
DR exercise fails late in the program | Low / High | Zone failover in every wave; DR dry run in the pilot | SRE lead | A DR test missed its recovery target

## Slide 17: Five decisions and what would change them
Decision | Options considered | Choice and why | Would change if
Migration strategy | Rehost all; replatform; refactor | Replatform. Managed services give HA and DR without code change | More than four applications cannot run unchanged
Sequencing | By tier; by platform; one cutover | A pilot, then one platform at a time. Least hybrid latency and coordination | Discovery shows heavy coupling across the platforms
Database target | Cloud SQL; AlloyDB; PostgreSQL on VMs | Cloud SQL. Built-in failover and the smallest operational change | An extension or performance gap appears in week 3
DR posture | Active-active; warm standby; backup only | Tiered: warm standby, pilot light, restore. Meets a 1-hour RTO without redesign | The business needs near-zero RTO for any application
Cutover style | Zero downtime; planned window | A planned window with a timed rehearsal. Simple, with a clean rollback | A Tier 1 application has no acceptable window
Each choice trades modernization for speed. Refactoring and active-active are logged as a backlog for after the program, not hidden.

## Slide 18: Decisions needed, and what gives first
Decision | Owner | Week
Recovery targets per tier | Business owners | 3
Containerize or rehost, per application | Cloud platform lead | 3
Primary and DR regions | Platform and security leads | 3
Team capacity and roadmap reductions | Executive sponsor | 4
Cutover windows and freeze calendar | Business owners | 4
Rollback point of no return per tier | Program and database leads | 9
Source decommission dates | Executive sponsor | 25
The date is fixed. In order, I would:
Re-sequence move groups inside a wave (my call)
Draw on the two contingency weeks (steering)
Add a third squad for Wave 2 (sponsor)
Defer Tier 3 DR automation (steering)
Defer a Tier 3 application (sponsor)
Week 10 is the first point where the date is confirmed with evidence. I would say so at kick-off.