## Schedule
WBS | Task | Owner | Start | Finish | Working days | Type | Predecessor
1 | GCP Migration Program |  | 2027-01-04 | 2027-07-02 | 130 | Summary
1.1 | M1 Mobilize and discover |  | 2027-01-04 | 2027-01-29 | 20 | Summary
1.1.1 | Confirm sponsor, governance and decision rights | Program lead | 2027-01-04 | 2027-01-08 | 5 | Task
1.1.2 | Order interconnect; open security baseline review | Cloud platform lead, Security lead | 2027-01-04 | 2027-01-08 | 5 | Task
1.1.3 | Inventory all 20 applications and dependencies | Application leads | 2027-01-04 | 2027-01-22 | 15 | Task
1.1.4 | Decide containerize or rehost per application; check database compatibility | Cloud platform lead, Database lead | 2027-01-11 | 2027-01-22 | 10 | Task
1.1.5 | Agree tiers and recovery targets | Program lead, business owners | 2027-01-18 | 2027-01-22 | 5 | Task
1.1.6 | Define move groups, wave plan, capacity and budget | Program lead | 2027-01-18 | 2027-01-29 | 10 | Task
1.1.7 | Approve target architecture and DR design | Cloud platform lead | 2027-01-25 | 2027-01-29 | 5 | Task
1.1.8 | G1 Baseline approved | Program lead | 2027-01-29 | 2027-01-29 | 0 | Gate
1.2 | M2 Foundations ready |  | 2027-01-18 | 2027-02-26 | 30 | Summary
1.2.1 | Build landing zone as code in two regions | Cloud platform lead | 2027-01-18 | 2027-02-12 | 20 | Task
1.2.2 | Bring up VPN, then interconnect | Cloud platform lead | 2027-01-25 | 2027-02-19 | 20 | Task
1.2.3 | Build CI/CD pipeline and base images | Cloud platform lead | 2027-01-25 | 2027-02-19 | 20 | Task
1.2.4 | Define database and replication patterns, backups | Database lead | 2027-02-01 | 2027-02-19 | 15 | Task
1.2.5 | Set up logging, monitoring, alerting, service levels | SRE lead | 2027-02-01 | 2027-02-26 | 20 | Task
1.2.6 | Security review and penetration test | Security lead | 2027-02-15 | 2027-02-26 | 10 | Task
1.2.7 | Deploy reference application end to end | Cloud platform lead | 2027-02-22 | 2027-02-26 | 5 | Task
1.2.8 | G2 Foundations accepted | Program lead | 2027-02-26 | 2027-02-26 | 0 | Gate
1.3 | M3 Pilot: 2 applications |  | 2027-02-15 | 2027-03-12 | 20 | Summary
1.3.1 | Build pilot applications in non-production; start replication | Squad 1 | 2027-02-15 | 2027-02-19 | 5 | Task
1.3.2 | Functional, integration and performance tests | Test lead | 2027-02-22 | 2027-02-26 | 5 | Task
1.3.3 | Rehearse cutover and rollback, timed | Squad 1, Database lead | 2027-02-22 | 2027-03-05 | 10 | Task
1.3.4 | Production cutover of pilot applications | Program lead | 2027-03-01 | 2027-03-05 | 5 | Task | G2 Foundations accepted
1.3.5 | Zone failover test; DR dry run; measure replica lag | SRE lead | 2027-03-01 | 2027-03-12 | 10 | Task
1.3.6 | Retrospective; update runbook, estimates, wave plan | Program lead | 2027-03-08 | 2027-03-12 | 5 | Task
1.3.7 | G3 Pilot live | Program lead | 2027-03-12 | 2027-03-12 | 0 | Gate
1.4 | M4 Wave 1: Platform A |  | 2027-03-15 | 2027-04-23 | 30 | Summary
1.4.1 | Build 8 applications in non-production; start replication | Squads 1 and 2, Platform A lead | 2027-03-15 | 2027-03-26 | 10 | Task | G3 Pilot live
1.4.2 | Test each move group | Test lead | 2027-03-22 | 2027-04-09 | 15 | Task
1.4.3 | Rehearse each cutover and rollback | Squads, Database lead | 2027-03-29 | 2027-04-16 | 15 | Task
1.4.4 | Cut over Tier 3 and Tier 2 applications (5) | Program lead | 2027-04-05 | 2027-04-16 | 10 | Task
1.4.5 | Cut over Tier 1 applications (3) | Program lead | 2027-04-12 | 2027-04-23 | 10 | Task
1.4.6 | Zone failover test per application | SRE lead | 2027-04-05 | 2027-04-23 | 15 | Task
1.4.7 | G4 Platform A complete | Program lead | 2027-04-23 | 2027-04-23 | 0 | Gate
1.5 | M5 Wave 2: Platform B |  | 2027-04-12 | 2027-06-04 | 40 | Summary
1.5.1 | Build 10 applications in non-production; start replication | Squads 1 and 2, Platform B lead | 2027-04-12 | 2027-05-07 | 20 | Task
1.5.2 | Test each move group | Test lead | 2027-04-19 | 2027-05-14 | 20 | Task
1.5.3 | Rehearse each cutover and rollback | Squads, Database lead | 2027-04-26 | 2027-05-21 | 20 | Task
1.5.4 | Cut over Tier 3 and Tier 2 applications (7) | Program lead | 2027-05-03 | 2027-05-21 | 15 | Task
1.5.5 | Cut over Tier 1 applications (3) | Program lead | 2027-05-17 | 2027-05-28 | 10 | Task
1.5.6 | Source set read-only and retained; contingency before G5 | Program lead | 2027-05-31 | 2027-06-04 | 5 | Task
1.5.7 | G5 All applications live | Program lead | 2027-06-04 | 2027-06-04 | 0 | Gate
1.6 | M6 Resilience proven |  | 2027-05-24 | 2027-06-18 | 20 | Summary
1.6.1 | Approve DR exercise scenario and success criteria | SRE lead, business owners | 2027-05-24 | 2027-05-28 | 5 | Task
1.6.2 | Load test the full estate at peak volume | Test lead | 2027-05-24 | 2027-06-04 | 10 | Task
1.6.3 | Regional failover exercise for Tier 1 and 2 | SRE lead | 2027-06-07 | 2027-06-11 | 5 | Task | G5 All applications live
1.6.4 | Timed backup restore for Tier 3 | Database lead | 2027-06-07 | 2027-06-11 | 5 | Task
1.6.5 | Fail back; fix findings; retest | SRE lead | 2027-06-14 | 2027-06-18 | 5 | Task
1.6.6 | Assemble evidence pack for risk and audit | Program lead | 2027-06-14 | 2027-06-18 | 5 | Task
1.6.7 | G6 Resilience proven | Program lead | 2027-06-18 | 2027-06-18 | 0 | Gate
1.7 | M7 Stabilize and hand over |  | 2027-06-14 | 2027-07-02 | 15 | Summary
1.7.1 | Hypercare for final wave; defect burn-down | Squads 1 and 2 | 2027-06-14 | 2027-06-25 | 10 | Task
1.7.2 | Hand over runbooks, on-call and dashboards; train operations | SRE lead | 2027-06-14 | 2027-06-25 | 10 | Task
1.7.3 | Set cost baseline and optimization backlog | Finance partner, Cloud platform lead | 2027-06-21 | 2027-06-25 | 5 | Task
1.7.4 | Agree dated decommission plan for source | Program lead | 2027-06-21 | 2027-06-25 | 5 | Task
1.7.5 | Closure report and lessons learned; contingency before G7 | Program lead | 2027-06-21 | 2027-07-02 | 10 | Task
1.7.6 | G7 Program closed | Program lead | 2027-07-02 | 2027-07-02 | 0 | Gate | G6 Resilience proven
Assumption: illustrative program start of Monday 4 January 2027; week 1 begins on that date. Gates fall on the Friday of their week.
Prepared by Balakrishna Pallapolu
Formulas:
Working days = NETWORKDAYS([Start],[Finish])